SEO & Content Strategy

Competitive Analysis, Keyword Plan & Quarterly Progress Tracker

Expertise Accelerated benchmarked against 18 competitors in outsourced accounting, bookkeeping and fractional CFO services

Prepared for: EA Team (Haroon)

Data source: Ahrefs Site Explorer, Keywords Explorer, Backlink Index & Crawled Pages (live pulls)

Baseline date: 23 August 2026 — all figures in Section 11 are measured from this date

Document type: Living tracker — re-run and update at each quarter end

Team status: All nine roles filled — eight full-time dedicated resources plus two CPA reviewers (≈8.3 FTE)

The single most urgent finding in this report EA's backlink profile contains at least 17 referring domains whose names explicitly advertise the sale of backlinks — including pbnseolinks.shop (PBN = Private Blog Network), buybacklinks.agency and buyseobacklinks.shop — alongside a further ~30 free directories and bookmark-spam sites. This is not a scattering of low-quality links. It is the signature of a paid link scheme, and it is the most likely explanation for why EA has 861 referring domains but a Domain Rating of only 24. No content investment will perform properly until this is addressed. Full detail and remediation plan in Section 5.

Contents & Ownership

Every section carries a red ownership tag directly above its heading, naming the team and the specific skillset required. Use the table below to route the document.

| # | Section | Owner | Skillset required |
| --- | --- | --- | --- |
| 1 | Executive Summary | Haroon (Leadership) | Strategic decision-making; no SEO skillset needed |
| 2 | Market Benchmark — 19 Domains | Tabish Khalid | Competitive analysis, Ahrefs proficiency |
| 3 | Site Architecture & Silo Structure | Talha Azeem + Usman Ali | Crawl analysis, redirects, schema, CMS access |
| 4 | Keyword Plan, Glossary & Content Gaps | Najma Furqan + Lavi Shamoon | Intent mapping, editorial planning, on-page SEO |
| 5 | Backlink Audit & Toxic Link Remediation | Talha Azeem | Disavow authoring, GSC admin access |
| 6 | Backlink Gap Analysis & Target List | Syed Ali | Outreach, partnerships, relationship building |
| 7 | Press Release Programme | Syed Ali + Hameed Ishaq | Media relations, journalist pitching, survey design |
| 8 | Additional Improvements | Mixed — see sub-tags | Technical SEO, content ops and analytics |
| 9 | Team Structure & Capacity Review | Haroon (Leadership) | Resource allocation, capacity and risk management |
| 10 | 12-Month Roadmap | Tabish Khalid | Programme management |
| 11 | Action Plan & Quarterly Progress Tracker | Tabish Khalid + all named owners | Programme governance, KPI tracking, accountability |
| A | Addendum A — D&V Philippines Study | Tabish Khalid + Haroon | Competitive intelligence, market positioning |
| B | Addendum B — Direct Briefs to Each Owner | Every named owner | Individual accountability, cross-functional collaboration |

Start here: Sections 5 and 3 close inside the first two weeks, Section 4 runs in parallel from day one, and Sections 6 and 7 from week two. Section 11 is the tracking instrument — it converts everything above into 34 dated actions against named individuals, with quarterly targets tied to each. Addendum B gives each named owner a direct brief.

Owner: Haroon (Leadership / CMO)  —  strategic decision-making and budget approval. No specialist SEO skillset required to read or act on this section.

# 1.  Executive Summary

Expertise Accelerated ranks 17th of the 19 outsourced-accounting domains benchmarked, with roughly 286 estimated monthly organic visits against a market led by Bench (52,353) and Pilot (50,359). Domain Rating is 24 against a peer median in the high-40s.

The analysis identified four distinct problems, and they are worth separating because they have very different fixes and very different urgency.

- A toxic backlink profile. EA has 861 referring domains — more than Maxim Liberty (831) or Optima Office (853), and within 27% of D&V Philippines (1,098). Yet EA's DR is 24 and D&V's is 51. Inspection of the profile shows why: at least 17 domains that openly sell links, roughly 16 free directories, six bookmark-spam sites, and nine topically unrelated domains including a gambling site and a German board-game forum. This is the highest-priority item in the report.

- Link equity trapped in redirects and errors. The two highest-authority URLs on the entire site — /accounts-payable/ and /general-accounting-and-bookkeeping/, both at URL Rating 11.7 — are 301 redirects. So is /fractional-cfo-services/ (UR 9.9), whose target keyword is worth 14,000 monthly searches at a $10 CPC. A Cloudflare artefact at UR 9.9 returns a 404. EA's strongest pages are the ones that no longer resolve.

- A completely flat site architecture. Every service, industry and location page sits at the root and carries an identical URL Rating of 6.9. Perfectly even distribution means no page is prioritised — the site is telling Google that all 30 pages are equally important, which is the same as saying none of them are.

- Pages that exist but do not rank. EA has published pages for manufacturing accounting, e-commerce accounting, Amazon accounting, trade promotions management, AP outsourcing, AR outsourcing and FP&A — and ranks for none of the corresponding head terms, several of which have keyword difficulty of 0 or 1. This is an optimisation problem, not a content-creation problem, and it is the cheapest win available.

The encouraging finding There are 15 keywords where EA already ranks in positions 11–28 — page two or three — representing 19,800 combined monthly searches. Most have a keyword difficulty below 8. These pages exist, are already indexed, and need optimisation rather than creation. Separately, the addendum benchmark against D&V Philippines shows their headline 16.7x traffic lead is misleading: 82% of it is Philippine-domestic job-seeker traffic that Ahrefs values at $251/month in total. In the United States, D&V draws 593 visits to EA's 260 — a 2.3x gap, closable within two to three quarters.

Recommended sequence: clean the link profile and fix the redirect/404 losses first (four to six weeks, low cost, no content required); optimise the 15 striking-distance pages and the seven non-ranking service pages second; then build the glossary and niche silos. Building content on top of the current foundation would waste most of the investment.

Team status: all nine roles are filled and eight are full-time dedicated resources — roughly 8.3 FTE. Technical, developer, design and analytics capacity all comfortably exceed what the workload requires, which is why the entire technical remediation block closes by 12 September. SME writing is the exception: one writer against a workload sized for two, which makes content volume the binding constraint on the programme (Section 9.3).

How to use this document: Section 11 converts all of the above into a 34-action register against named individuals, a quarter-by-quarter projection of every critical statistic, and a map showing whose underperformance shows up in which metric. Re-run the Ahrefs pulls each quarter and complete the scorecard — the numbers themselves become the accountability mechanism. Addendum B addresses each owner directly on what is required of them.

Owner: Tabish Khalid (Head of SEO & Content)  •  Skillset: Ahrefs proficiency, benchmark reporting, share-of-voice tracking. Re-run quarterly with Abdullah Shekha.

# 2.  Market Benchmark — 19 Domains

Pulled from Ahrefs, 22 August 2026, subdomains mode, both protocols. “Est. value” is Ahrefs' estimate of what the equivalent traffic would cost through paid search.

| # | Company | Domain | DR | Organic traffic/mo | Organic keywords | Kws #1–3 | Est. value /mo | Ref. domains |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Bench | bench.co | 77 | 52,353 | 7,800 | 2,257 | $155,899 | 8,365 |
| 2 | Pilot | pilot.com | 70 | 50,359 | 5,874 | 1,798 | $204,050 | 5,055 |
| 3 | Paro | paro.ai | 73 | 14,766 | 2,325 | 699 | $47,967 | 2,249 |
| 4 | Belay Solutions | belaysolutions.com | 71 | 14,188 | 377 | 125 | $15,982 | 3,814 |
| 5 | TOA Global | toaglobal.com | 50 | 13,856 | 1,683 | 593 | $43,282 | 3,246 |
| 6 | NOW CFO | nowcfo.com | 46 | 5,206 | 571 | 224 | $25,091 | 1,372 |
| 7 | D&V Philippines | dvphilippines.com | 51 | 4,783 | 633 | 168 | $7,366 | 1,098 |
| 8 | Supporting Strategies | supportingstrategies.com | 47 | 3,290 | 97 | 23 | $9,240 | 1,312 |
| 9 | inDinero | indinero.com | 64 | 2,804 | 1,181 | 339 | $8,454 | 2,298 |
| 10 | Maxim Liberty | bookkeeping-services.com | 30 | 2,289 | 491 | 155 | $10,358 | 831 |
| 11 | Bookkeeper360 | bookkeeper360.com | 54 | 2,274 | 294 | 66 | $9,343 | 1,310 |
| 12 | Escalon Services | escalon.services | 55 | 1,280 | 346 | 135 | $2,952 | 1,296 |
| 13 | AAFCPA | aafcpa.com | 41 | 1,197 | 210 | 62 | $3,033 | 1,036 |
| 14 | Fully Accountable | fullyaccountable.com | 42 | 1,157 | 208 | 78 | $2,709 | 1,185 |
| 15 | Optima Office | optimaoffice.com | 30 | 959 | 231 | 105 | $6,087 | 853 |
| 16 | Bookkeeper.com | bookkeeper.com | 39 | 298 | 40 | 13 | $1,050 | 2,569 |
| 17 | Expertise Accelerated | expertiseaccelerated.com | 24 | 286 | 115 | 16 | $1,467 | 861 |
| 18 | 2Go Advisory Group | 2goadvisorygroup.com | 5 | 124 | 28 | 14 | $560 | 956 |
| 19 | Merritt Bookkeeping | merrittbookkeeping.com | 36 | 106 | 12 | 4 | $557 | 772 |

## What separates the leaders

- Pilot — one listicle, “best small business accounting software” (60,000 searches), drives 19,037 visits per month, out-trafficking EA's entire domain by roughly 66x. Their glossary captures definitional demand cheaply: “outsourced cfo” pulls 1,177 visits, “fractional cfo” 539.

- Bench — evergreen accounting fundamentals. “Debits vs. credits” pulls 6,190 visits across 454 keywords; “liabilities in accounting” 3,183 visits across 378 keywords. Their homepage alone ranks for 271 non-branded keywords.

- Paro — same playbook, smaller scale. A “trial balance” definition page (14,000 searches) out-performs every one of their own service pages.

- NOW CFO — the most instructive comparison for EA, because at DR 46 they are not an unreachable outlier. They reached 5,206 visits largely through chambers of commerce, industry associations, podcast appearances and regional press. That playbook is detailed in Section 6.2.

- D&V Philippines — EA's closest like-for-like competitor by service mix. Analysed in full in the Addendum at the end of this document.

The pattern: in every case the traffic engine is broad educational content, not service pages. EA has 30 service pages averaging 2 keywords each. The leaders have fewer service pages and far more educational content, each piece ranking for hundreds of terms.

Owner: Talha Azeem (Technical SEO / Content Strategist) + Usman Ali (Web Developer)  •  Skillset: crawl analysis, 301 redirect mapping, canonicalisation, internal-link architecture, BreadcrumbList schema. Both full-time; production access confirmed.

# 3.  Site Architecture & Silo Structure

Question asked: is silo structure important or not? Answer: important for EA specifically, but not for the reason it is usually sold — and the crawl data makes the case far more concretely than theory would.

## 3.1  The honest case against over-investing in silos

Silo structure is often marketed as a ranking factor in its own right. It is not. Google does not award points for a tidy folder hierarchy, and URL depth has minimal direct effect on rankings. Large sites rank well with flat architectures and poor ones rank badly with immaculate hierarchies. Any agency proposing a costly URL migration as a primary SEO deliverable is selling the wrong thing — and migrations carry real risk of broken redirects and lost equity.

## 3.2  What the crawl found at EA — three concrete problems

### Problem 1: link equity is trapped in redirects and a 404

URL Rating measures a page's individual backlink strength. Sorting EA's crawled pages by UR reveals that the strongest URLs on the site do not resolve:

| URL | URL Rating | Status | Why it matters |
| --- | --- | --- | --- |
| /accounts-payable/ | 11.7 | 301 redirect | Highest-equity URL on the site — and it is a redirect |
| /general-accounting-and-bookkeeping/ | 11.7 | 301 redirect | Joint-highest equity — also a redirect |
| /cdn-cgi/l/email-protection | 9.9 | 404 error | Cloudflare artefact with accumulated links, returning 404 |
| /fractional-cfo-services/ | 9.9 | 301 redirect | Target term worth 14,000 searches/mo at $10 CPC |
| /author/najmafurqan/ | 8.4 | 301 redirect | Author archive holding equity |
| /cash-flow-projections/ | 7.6 | 301 redirect | Redirected service page |
| /inventory-management/ | 7.6 | 301 redirect | Duplicate of /inventory-management-services/ |
| /white-papers/ | 7.6 | 301 redirect | Resource hub redirected away |
| /fractional-cpg-cfo-services/ | 6.9 | 301 redirect | EA's most differentiated service — redirected |
| /blogs/ | 6.9 | 301 redirect | Duplicate of /blog/ |

This is the most concrete, lowest-effort finding in the report. EA's two highest-equity URLs (UR 11.7) are redirects, sitting above the homepage itself (UR 7.7). Every 301 hop dissipates some equity, and the 404 at UR 9.9 wastes it entirely. Restoring /fractional-cfo-services/ as a live, optimised page is particularly urgent: “fractional cfo” is 14,000 searches per month at a $10 CPC and EA does not rank for it at all.

### Problem 2: the architecture is perfectly, uselessly flat

Almost every page on the site carries an identical URL Rating of 6.9 — service pages, industry pages, location pages, the contact page and the team page alike. Perfectly even internal link distribution is not neutral; it actively prevents any page from being prioritised. The homepage sits at 7.7, barely distinguishable.

The URL structure confirms it. Everything lives at the root, with no parent paths grouping related content:

| Group | URLs (all at root level — no parent path) |
| --- | --- |
| Services | /accounts-payable-outsourcing-services/, /accounts-receivable-outsourcing-services/, /general-accounting-and-bookkeeping-services/, /financial-planning-services/, /internal-audit-support/, /external-audit-support/, /internal-controls-sox-services/, /cash-flow-management-services/, /sales-order-processing-invoicing/, /accounting-staff-augmentation/, /inventory-management-services/, /demand-and-supply-planning/, /business-process-optimization/ |
| Industries | /consumer-packaged-goods/, /manufacturing-accounting/, /retail-wholesale-accounting/, /ecommerce-accounting/, /amazon-accounting/, /restaurant-accounting/, /real-estate-accounting/, /trade-promotions-management/ |
| Locations | /accounting-services-in-new-york/, /accounting-services-in-chicago/, /accounting-services-in-los-angeles/, /accounting-services-in-houston/, /accounting-services-in-atlanta/, /accounting-services-in-austin/, /accounting-services-in-san-diego/ |
| Resources | /blog/, /case-studies/, /resources/, /our-team/, /contact-us/, /book-a-free-consultation/ |

Consequence: nothing signals that /consumer-packaged-goods/ and /trade-promotions-management/ are related, or that the blog posts about CPA costs should be feeding the pricing service page. With a Domain Rating of 24 there is very little authority to distribute — and it is currently being spread evenly across 30+ pages instead of concentrated behind the handful that could actually rank.

### Problem 3: pages exist but do not rank for their own head terms

EA has published /manufacturing-accounting/, /ecommerce-accounting/, /amazon-accounting/, /trade-promotions-management/, /accounts-payable-outsourcing-services/, /accounts-receivable-outsourcing-services/ and /financial-planning-services/. It ranks for none of the corresponding head terms — several of which carry a keyword difficulty of 0 or 1. The pages are isolated: no supporting content, no internal links concentrating relevance, no topical depth signalling expertise.

## 3.3  Recommended architecture

Adopt hub-and-spoke topical clusters. The clusters matter more than the URL paths — if migration looks risky, keep the URLs and implement the silo through internal linking and navigation alone. That captures most of the benefit at a fraction of the risk.

Proposed pillars:

- Outsourced Accounting & Bookkeeping — the broad commercial pillar

- Fractional CFO, Controllership & FP&A — high-value advisory (restore the 301'd URL here)

- CPG & Trade Promotion Management — EA's differentiated wedge

- Manufacturing & Inventory Accounting — largest niche opportunity at 3,490 searches

- Retail, E-commerce & Amazon Seller Finance

- Accounting Glossary & Resources — the top-of-funnel traffic engine

Rules for each cluster:

- One comprehensive pillar page per cluster (2,500–4,000 words) targeting the highest-volume commercial term.

- 8–15 supporting pages per pillar, each targeting one specific sub-topic or question.

- Every supporting page links up to its pillar with descriptive anchor text; the pillar links down to every supporting page.

- Cross-silo links only where genuinely useful to a reader.

- Breadcrumb navigation with BreadcrumbList schema so the hierarchy is machine-readable.

- Location pages become spokes of the relevant industry silo — Chicago already positions on manufacturing and logistics, San Diego on healthcare and biotech, so the vertical mapping exists and simply is not linked.

Priority: high — but the redirect and 404 cleanup in Problem 1 comes first, is far cheaper, and can be completed in days rather than weeks.

Owner: Najma Furqan (Editor) + Lavi Shamoon (SME Writer), with Tabish Khalid on keyword strategy  •  Skillset: search-intent mapping, SERP-format matching, editorial calendar planning, on-page optimisation. Every page requires CPA sign-off from Haroon or Adeela before publication (Action A3).

# 4.  Keyword Plan, Glossary & Content Gaps

All volumes, difficulty scores and CPC figures below were pulled from Ahrefs Keywords Explorer for the United States. Difficulty is on a 100-point scale; a score under 10 is achievable for a low-authority domain with a well-built page.

## 4.1  Priority 1 — striking-distance pages (fastest wins)

These are keywords EA already ranks for in positions 11–28. The pages exist and are indexed; they need optimisation, internal links and content expansion rather than creation. Combined volume: 19,800 searches per month, most at difficulty below 8.

| Keyword | Volume | Current position | Difficulty | Current traffic | Priority |
| --- | --- | --- | --- | --- | --- |
| operating income | 8,600 | 28 | 3 | 0 | High |
| what is operating income | 1,900 | 17 | 2 | 0 | High |
| accounts receivable services | 1,800 | 20 | 7 | 6 | High |
| operating income formula | 1,400 | 19 | 3 | 0 | High |
| financial and managerial accounting | 1,200 | 21 | 1 | 1 | High |
| cpa vs accountant | 1,000 | 24 | 1 | 1 | High |
| cpa cost | 700 | 25 | 8 | 0 | Medium |
| financial vs managerial accounting | 600 | 15 | 1 | 5 | High |
| retail accounting | 500 | 22 | 4 | 1 | Medium |
| managerial accounting vs financial accounting | 500 | 17 | 2 | 0 | Medium |
| accountants for small business | 450 | 16 | 2 | 4 | Medium |
| accountant vs cpa | 450 | 15 | 0 | 3 | High |
| bookkeeping outsourcing services | 400 | 13 | 19 | 6 | High |
| online accounts payable services | 200 | 11 | 8 | 5 | High |
| rfp in finance | 100 | 11 | 0 | 3 | Medium |

Note the pattern: “operating income” (8,600 searches, difficulty 3) sits at position 28 and earns zero traffic. Four of the top six entries are the operating-income and managerial-accounting clusters, all at difficulty 1–3. These should be consolidated into two strong pillar pages rather than left as scattered thin posts.

## 4.2  Priority 2 — commercial money terms EA does not rank for

These are the transactional and commercial-investigation terms that convert. The right-hand column shows how many EA already has a page for but is not ranking with — those are optimisation jobs, not writing jobs.

| Keyword | Volume | KD | CPC | Traffic potential | EA currently ranks? |
| --- | --- | --- | --- | --- | --- |
| fractional cfo | 14,000 | 11 | $10.00 | 2,000 | No — URL is a 301 |
| outsourced bookkeeping | 5,800 | 9 | $17.00 | 4,600 | No |
| outsourced accounting services | 4,300 | 8 | $0.80 | 700 | No |
| outsourced cfo | 4,000 | 2 | $9.00 | 2,500 | No |
| fractional cfo services | 3,700 | 19 | $6.00 | 3,000 | No — URL is a 301 |
| bookkeeping services for small business | 3,300 | 15 | $2.50 | 14,000 | No |
| cfo services | 2,700 | 1 | $1.40 | 1,000 | No |
| outsourced accounting | 2,500 | 9 | $0.90 | 3,500 | No |
| accounts payable automation | 2,200 | 33 | $0.60 | 4,500 | No |
| accounting outsourcing | 2,100 | 3 | $5.00 | 3,500 | No |
| virtual cfo | 1,200 | 14 | $8.00 | 1,500 | No |
| inventory accounting | 1,100 | 3 | $1.60 | 450 | No |
| month end close process | 700 | 14 | $3.00 | 1,700 | No |
| manufacturing accounting | 700 | 0 | $3.50 | 700 | No — page exists, not ranking |
| accounts receivable outsourcing | 600 | 1 | $1.00 | 800 | No — page exists, not ranking |
| trade promotion management | 600 | 6 | $5.00 | 1,000 | No — page exists, not ranking |
| ecommerce accounting | 600 | 8 | $25.00 | 500 | No — page exists, not ranking |
| outsourced controller | 500 | 0 | $8.00 | 350 | No |
| offshore accounting services | 450 | 7 | $14.00 | 250 | No |
| standard costing | 400 | 3 | $1.20 | 350 | No |
| amazon seller accounting | 350 | 0 | $15.00 | 250 | No — page exists, not ranking |
| deduction management | 250 | 1 | $10.00 | 100 | No |
| trade spend management | 200 | 1 | $8.00 | 350 | No |
| cpg accounting | 150 | 0 | $8.00 | 30 | Yes — position 7 |
| fp&a services | 150 | 0 | $7.00 | 200 | No — page exists, not ranking |
| outsourced accounts payable | 100 | 1 | $20.00 | 1,000 | No — page exists, not ranking |

Read this table carefully — it contains the whole strategy • “fractional cfo” — 14,000 searches, $10 CPC, difficulty 11. EA's page for this is a 301 redirect. Restoring and optimising it is the single highest-value action available. • “outsourced cfo” (4,000, KD 2) and “cfo services” (2,700, KD 1) are near-uncontested and EA has no page for either. • Seven highlighted rows are terms where EA has already built the page and simply is not ranking — including manufacturing accounting (KD 0), amazon seller accounting (KD 0) and fp&a services (KD 0). • Highest CPCs in the set are ecommerce accounting ($25), outsourced accounts payable ($20), outsourced bookkeeping ($17) and offshore accounting services ($14) — a reliable signal of buyer value.

## 4.3  The glossary — 31 validated terms

Glossary and definition pages are the highest-efficiency format available to a low-authority domain: they target informational queries wanting a direct answer, are short to produce, are rarely contested by service providers, and accumulate internal-link equity that can be routed to commercial pages. Pilot's glossary demonstrates the economics — their “outsourced cfo” entry alone pulls 1,177 visits per month.

The list below is ordered by search volume. Every figure is Ahrefs-verified. Combined volume across the 31 terms exceeds 250,000 monthly searches.

| Term | Volume | KD | Traffic potential | Recommended format |
| --- | --- | --- | --- | --- |
| ebitda | 149,000 | 26 | 8,100 | Definition + calculator |
| gross margin | 23,000 | 15 | 900 | Definition + formula |
| working capital | 20,000 | 43 | 4,200 | Pillar guide |
| cost of goods sold | 19,000 | 27 | 12,000 | Definition + COGS calculator |
| general ledger | 14,000 | 14 | 1,600 | Definition + example |
| deferred revenue | 13,000 | 5 | 2,500 | Definition — low difficulty, high volume |
| inventory turnover ratio | 12,000 | 16 | 12,000 | Calculator + benchmark data |
| chart of accounts | 9,800 | 12 | 2,100 | Definition + downloadable template |
| bank reconciliation | 8,100 | 12 | 4,800 | How-to + template |
| accrued expenses | 5,500 | 22 | 1,400 | Definition |
| what is fp&a | 3,700 | 10 | 1,200 | Definition — feeds FP&A service page |
| days sales outstanding | 3,500 | 21 | 2,800 | Calculator + DSO benchmarks |
| burn rate | 3,500 | 24 | 1,500 | Definition + calculator |
| balance sheet vs income statement | 3,100 | 4 | 2,600 | Comparison — very low difficulty |
| revenue recognition | 2,600 | 18 | 9,300 | Pillar guide (ASC 606) |
| accrual vs cash accounting | 2,500 | 12 | 4,200 | Comparison guide |
| what is a fractional cfo | 2,300 | 16 | 5,800 | Definition — feeds CFO pillar |
| accounts payable process | 1,700 | 3 | 3,100 | Process guide — feeds AP service page |
| bookkeeping vs accounting | 1,500 | 6 | 1,400 | Comparison guide |
| landed cost | 1,200 | 11 | 400 | Definition — manufacturing silo |
| cash flow forecasting | 1,100 | 16 | 1,600 | Guide + template |
| accounts receivable process | 900 | 4 | 1,100 | Process guide — feeds AR service page |
| fixed asset accounting | 800 | 12 | 1,600 | Definition |
| internal controls accounting | 700 | 2 | 400 | Guide — feeds SOX service page |
| three way match | 450 | 3 | 2,400 | Definition — feeds AP service page |
| purchase order process | 450 | 4 | 150 | Process guide |
| gaap compliance | 400 | 30 | 3,200 | Pillar guide |
| what is a controller in accounting | 300 | 2 | 1,800 | Definition — feeds controller page |
| how much does bookkeeping cost | 200 | 4 | 1,400 | Pricing guide |
| how much does outsourced accounting cost | 100 | 2 | 100 | Pricing guide |
| work in process accounting | 90 | 20 | 1,300 | Definition — manufacturing silo |

### How to sequence the glossary build

- Start with low-difficulty, high-volume: “deferred revenue” (13,000 searches, KD 5), “balance sheet vs income statement” (3,100, KD 4), “accounts payable process” (1,700, KD 3), “accounts receivable process” (900, KD 4), “internal controls accounting” (700, KD 2), “three way match” (450, KD 3). These are winnable at DR 24.

- Defer the hardest: “working capital” (KD 43), “gaap compliance” (KD 30), “cost of goods sold” (KD 27) and “ebitda” (KD 26) are worth targeting eventually but not in the first two quarters.

- Prioritise terms that feed money pages: “what is fp&a”, “accounts payable process”, “accounts receivable process”, “three way match”, “what is a controller in accounting” and “what is a fractional cfo” each link naturally to an EA service page. These do double duty — traffic plus internal equity routing.

- Add templates and calculators: chart of accounts template, DSO calculator, inventory turnover calculator, cash flow forecast template. These earn links at a much higher rate than plain definitions.

## 4.4  The niche land-grab — now quantified

These clusters are where EA can rank fastest because the competitor set has effectively no coverage:

| Cluster | Verified terms (volume, difficulty) | Combined volume | Difficulty range |
| --- | --- | --- | --- |
| Trade promotion & deduction | trade promotion management (600, KD 6), trade spend management (200, KD 1), deduction management (250, KD 1) | 1,050 | 1–6 |
| CPG / FMCG finance | cpg accounting (150, KD 0) + long-tail cluster | 150+ | 0 |
| Manufacturing & inventory | manufacturing accounting (700, KD 0), inventory accounting (1,100, KD 3), standard costing (400, KD 3), landed cost (1,200, KD 11), WIP accounting (90, KD 20) | 3,490 | 0–20 |
| E-commerce & Amazon | ecommerce accounting (600, KD 8), amazon seller accounting (350, KD 0) | 950 | 0–8 |
| Controllership & FP&A | outsourced controller (500, KD 0), fp&a services (150, KD 0), month end close process (700, KD 14) | 1,350 | 0–14 |

Roughly 7,000 monthly searches at difficulty 0–20, in categories where EA has genuine operating expertise and no competitor has built content. Manufacturing is the largest single opportunity at 3,490 searches, and EA's /manufacturing-accounting/ page already exists.

## 4.5  Intent framework for the editorial calendar

- Informational (~60% of output): definitions, “how to”, “X vs Y”, templates, calculators. Purpose is reach and link acquisition; these should not be judged on direct conversion.

- Commercial investigation (~30%): “best X services”, “how much does X cost”, “X vs in-house”, provider comparisons. Highest-value type — the searcher is actively evaluating. EA's best-performing existing page (“how much does a CPA cost”) is exactly this format, which is the proof case.

- Transactional (~10%): the money pages in section 4.2. Few in number, heavily internally linked from the other two tiers.

A recurring error to avoid: writing service-page copy for informational queries. EA's thin service pages are competing for terms whose SERPs are dominated by educational content, which is why they rank for one or two keywords each. Match the format to the intent the SERP is already rewarding.

Owner: Talha Azeem (Technical SEO), with Haroon authorising vendor termination  •  Skillset: backlink profile auditing, spam-signal classification, disavow file authoring. Requires Google Search Console admin access. Highest priority in this report.

# 5.  Backlink Profile Audit & Toxic Link Remediation

EA has 861 referring domains and 1,982 backlinks. On volume alone that should support a Domain Rating in the 40s. It supports 24. Reviewing the referring domains explains why.

| Category | Count (sample) | Examples found in EA's live backlink profile |
| --- | --- | --- |
| Explicit link-selling sites | 17 | pbnseolinks.shop, buybacklinks.agency, buyseobacklinks.shop, authoritybacklinks.shop, backlinker.shop, ranklinkpro.shop, linkrankpro.shop, seolinkpro.shop, linkseopro.shop, rankxlinks.shop, ranklinkerpro.shop, ranklinkx.shop, linkrankboost.shop, rankboostly.shop, seorankflow.shop, rank-top.click, kingranks.com |
| Free business directories | 16 | fyple.com, iformative.com, expressbusinessdirectory.com, whatsyourhours.com, dealerbaba.com, yplocal.com, bizlistusa.com, businesslistus.com, golocalezservices.com, getlisteduae.com, bizidex.com, weboworld.com, ezilon.com, freelistingusa.com, techdirectory.io, bizify.co.uk |
| Bookmark / article spam | 6 | socialbookmarkssite.com, video-bookmark.com, thezenweb.com, blogminds.com, apsense.com, leasedadspace.com |
| Topically irrelevant | 9 | janefonda.com, bettingbase.net (gambling), chillspot1.com, getbb.ru (Russian forum), legenden-von-andor.de (board games), onvasortir.com (French events), m5stack.com (IoT hardware), codeigniter.com (PHP framework), edn.com (electronics) |
| Ahrefs-flagged spam | 3 | pages.dev, rankyour.website, factmags.com |

This is not ambiguous Seventeen referring domains have names that explicitly advertise selling backlinks. One is literally called pbnseolinks.shop — PBN stands for Private Blog Network, a technique Google's spam policies name directly. Link schemes of this kind are a documented violation of Google's guidelines. The consequences range from the links simply being ignored (best case, meaning the money spent achieved nothing) to an algorithmic suppression of the whole domain (worst case, and consistent with EA's DR of 24 on 861 referring domains). This needs to be addressed before any content investment, because content published onto a suppressed domain will underperform regardless of quality.

## 5.1  Remediation plan

- Export the full referring-domain list from Ahrefs and classify every domain: keep, ignore, or disavow. Roughly 50 domains identified in this analysis are clear disavow candidates; a full pass across all 861 will likely surface more.

- File a disavow through Google Search Console at domain level for the link-selling sites, PBNs and Ahrefs-flagged spam. Be conservative with genuine directories — disavowing too aggressively can remove links that were helping.

- Terminate any active link-building vendor arrangement. The .shop domain cluster indicates an ongoing or recent paid campaign. If it is still running, disavowing while it continues is pointless.

- Convert the salvageable directory presences into lead sources. Clutch, Crunchbase, G2 and ProvenExpert pass no link equity but do drive qualified referral traffic. Treat them as a sales channel and complete the profiles properly.

- Redirect all future link acquisition to the target list in Section 6. No further directory submissions, no paid link packages, no reciprocal exchanges.

Expected effect: disavowal does not add authority — it removes drag. The realistic outcome is that subsequent legitimate link acquisition starts converting into Domain Rating movement instead of being offset. Allow one to three months for Google to reprocess. This is why the Section 11 projection shows DR barely moving through 30 September 2026 and only gaining materially from December onward — and why a near-flat DR at the first checkpoint is not evidence that Talha or Syed Ali have underperformed.

## 5.2  What a healthy profile looks like

For contrast, Pilot's strongest links come from partner ecosystems (Stripe 78 dofollow links at DR 95, Zendesk 14, Gusto, Ramp, Deel, Salesforce), earned press (NYT, Fortune, TechCrunch) and academic citations (MIT, Rice). Not one free directory appears in their top 40 — and Stripe alone is worth more than EA's entire directory footprint.

Owner: Syed Ali (Director of Marketing — Digital PR / Link Acquisition)  •  Skillset: prospect research, cold outreach, partnership and association management, podcast booking. Relationship-driven — not a technical role.

# 6.  Backlink Gap Analysis & Target List

## 6.1  Domains linking to competitors but not to EA

Cross-referencing the referring domains of Pilot, Paro, NOW CFO and D&V Philippines against EA's own profile produces the following list. Domains linking to two or more competitors have demonstrated willingness to link to this category, which makes them the highest-conversion outreach targets available.

| Domain | DR | Links to | Comps | Likely route in |
| --- | --- | --- | --- | --- |
| fortune.com | 91 | Pilot, Paro, NOW CFO | 3 | Earned press / contributed |
| substack.com | 94 | Pilot, Paro, NOW CFO | 3 | Newsletter mentions |
| builtin.com | 86 | Pilot, Paro, NOW CFO | 3 | Employer-brand profile |
| forbes.com | 94 | Paro, NOW CFO | 2 | Council membership / earned |
| inc.com | 91 | Paro, NOW CFO | 2 | Contributed column |
| entrepreneur.com | 91 | Pilot, Paro | 2 | Contributed column |
| hubspot.com | 93 | Pilot, Paro | 2 | Co-marketing / guest content |
| gusto.com | 86 | Pilot, Paro | 2 | Partner ecosystem |
| squarespace.com | 95 | Pilot, NOW CFO | 2 | Partner ecosystem |
| joinhomebase.com | 78 | Pilot, Paro | 2 | Partner ecosystem |
| welcometothejungle.com | 86 | Pilot, Paro | 2 | Employer-brand profile |
| iheart.com | 91 | Pilot, Paro | 2 | Podcast syndication |
| appsruntheworld.com | 69 | D&V, NOW CFO | 2 | Software-vendor profile |
| analyticsinsight.net | 80 | D&V, Paro | 2 | Contributed article |

Fortune, Substack and BuiltIn each link to three of the four competitors analysed and not to EA. Forbes, Inc. and Entrepreneur link to two each — all three operate paid contributor councils, which is a direct and predictable route to a DR 91+ dofollow link.

## 6.2  The NOW CFO playbook — most replicable for EA

NOW CFO is the most instructive competitor in the set because they are not an unreachable outlier: DR 46, 1,372 referring domains, 5,206 monthly visits. Their link profile shows exactly how a mid-sized professional services firm builds authority without Silicon Valley press coverage:

| Referring domain | DR | Dofollow links | Channel |
| --- | --- | --- | --- |
| chambermaster.com | 78 | 59 | Chamber of Commerce member directories |
| acg.org | 72 | 60 | Association for Corporate Growth membership |
| growthzoneapp.com | 79 | 23 | Association management platform listings |
| promatcher.com | 62 | 12 | Professional services marketplace |
| birdeye.com | 86 | 10 | Reputation / review platform |
| eonetwork.org | 76 | 4 | Entrepreneurs' Organization |
| cbinsights.com | 86 | 4 | Company intelligence profile |
| memberzone.com | 62 | 3 | Association member directory |
| buzzsprout.com / libsyn.com / transistor.fm | 91 / 91 / 86 | 9 total | Podcast guest appearances |
| kutv.com / 25newsnow.com / sandiegomagazine.com | 77 / 67 / 76 | 2,811 total | Regional press coverage |

The lesson: chambers of commerce (59 links via ChamberMaster), industry associations (60 via ACG alone, plus GrowthZone and MemberZone), podcast appearances (three hosting platforms), and regional press. None of this requires a funding announcement or a national news hook. All of it is available to EA today, and EA has essentially none of it.

## 6.3  Prioritised target list

| Category | Specific targets | Why it works | Timing | Est. links |
| --- | --- | --- | --- | --- |
| Accounting software partner directories | NetSuite, Sage Intacct, QuickBooks ProAdvisor, Xero Partner, Bill.com, Ramp, Brex | Dofollow, topically exact, permanent, free | Immediate | 20–35 |
| TPM / CPG software ecosystems | Vividly, Cresicor, Kantar, Circana, Repsly partner pages | Zero competitor presence; EA's exact niche | Immediate | 5–10 |
| Chambers & associations | Local chambers via ChamberMaster, ACG, AICPA, IMA, Consumer Brands Association, NACM | NOW CFO's proven playbook — 140+ links from this channel alone | Month 1–3 | 40–80 |
| Review & comparison platforms | G2, Capterra, TrustRadius, upgraded Clutch profile | Buyer-intent referral traffic even where nofollow | Immediate | 5–10 |
| Podcast circuit | CFO / CPG-finance / manufacturing podcasts (Buzzsprout, Libsyn, Transistor-hosted) | Show-notes dofollow links plus direct pipeline | Month 2 onward | 15–30/yr |
| Contributed columns | Forbes / Entrepreneur / Inc. councils, Analytics Insight, industry trade press | DR 91+ dofollow; three competitors already use this | Month 3 onward | 8–15/yr |
| Regional & trade press | Connecticut/Stamford business press, CPG and manufacturing trade titles | NOW CFO earned 2,800+ links regionally | Month 3 onward | 10–20 |
| Original research assets | Annual CPG Finance Benchmark Report; trade-spend leakage calculator | Compounds — earns links passively for years | Q2 onward | 50–150 |

### The partner-ecosystem play, specifically

Every accounting platform EA works in — NetSuite, Sage Intacct, QuickBooks, Xero, Bill.com — operates a partner directory with dofollow listings. So do the spend-management platforms (Ramp, Brex) and, critically for EA's niche, the TPM vendors (Vividly, Cresicor). These links are topically perfect, permanent, free, and require only that EA complete a profile and maintain the relationship.

D&V Philippines has done this and leads with it in their positioning as a Xero Gold Partner. EA should audit every platform it holds a certification or partnership with and claim the listing.

## 6.4  What to stop doing

- No further free-directory or listing-site submissions. This channel is saturated and is the reason the profile has volume without strength.

- No paid guest-post networks or link packages — the documented source of the current problem.

- No reciprocal link exchanges with unrelated businesses.

- Treat any vendor promising a fixed number of links per month as a red flag; that pricing model only works using the networks that caused this.

Owner: Syed Ali (Director of Marketing), with Hameed Ishaq on report design and Haroon on survey sign-off  •  Skillset: media relations, journalist pitching, contributed-column writing, survey design. Same owner as Section 6 — sequence the two so outreach is not duplicated.

# 7.  Press Release Programme

## 7.1  How many press releases?

Recommendation: 16–20 announcements per year, with only 4 of them going through a paid wire.

Measuring a PR programme by release count is the wrong frame, and it is worth being direct about why in EA's case specifically. Wire distribution produces syndicated copies of a release across low-quality news aggregators. Those links are almost universally nofollow or from thin syndication domains. They generate a visible spike in referring domains and essentially no authority.

Given that EA's core problem is already a profile inflated by volume without strength — and that an existing referring domain, abnewswire.com, indicates wire distribution has been used before — a high-volume wire programme would deepen the exact problem this report identifies. It would add hundreds of low-value referring domains to a profile already being penalised for exactly that composition.

What moves Domain Rating is earned coverage: a journalist at a publication with real editorial standards choosing to cite EA. That requires something genuinely newsworthy, which caps the sustainable cadence at roughly one substantive story every three to four weeks.

| Tier | Cadence | Content type | Distribution method | SEO value |
| --- | --- | --- | --- | --- |
| Tier 1 — Earned business/trade press | 4–6 / yr | Funding, major client wins, proprietary research, executive hires | Direct journalist pitching (no wire) | Very high |
| Tier 2 — Industry trade media | 6–8 / yr | CPG/manufacturing finance commentary, benchmark data | Editor relationships + contributed columns | High |
| Tier 3 — Wire distribution | 4 / yr | Milestones, certifications, partnerships, expansion | Paid newswire | Low–moderate |
| Tier 4 — Owned research | 2 / yr | Original survey data (CPG finance cost benchmarks) | Gated report + press outreach | Very high |

Total: 16–20 announcements annually. Four wire releases for milestones where broad visibility matters more than link equity; the remaining 12–16 pitched directly to editors. Budget effort in inverse proportion to release count — one placement in CFO Dive is worth more than twelve wire distributions.

## 7.2  Where to place them

| Publication / outlet | Audience | Route in | Why it matters for EA |
| --- | --- | --- | --- |
| CFO Dive | Finance leadership | Editorial pitch | Reaches exact ICP; strong topical relevance |
| CFO.com | Finance leadership | Editorial + contributed | Category authority with CFO buyers |
| Accounting Today | Accounting profession | Editorial + contributed | Category authority; high topical trust |
| Journal of Accountancy (AICPA) | Accounting profession | Contributed / cited research | Highest topical authority in the field |
| Food Dive / Grocery Dive | CPG & grocery trade | Editorial pitch | Direct line to EA's CPG buyers |
| Consumer Goods Technology | CPG operations & tech | Contributed / commentary | TPM and trade-spend audience |
| IndustryWeek | Manufacturing | Contributed column | Manufacturing-accounting positioning |
| Supply Chain Dive | Supply chain | Editorial pitch | Adjacent to EA's supply-chain services |
| Forbes / Entrepreneur / Inc. councils | Business general | Paid council membership | DR 91–94 dofollow; 3 competitors already there |
| Analytics Insight | Business tech | Contributed article | D&V and Paro both have links here |
| Business Wire / PR Newswire | Wire distribution | Paid | Syndication reach; mostly nofollow |
| EIN Presswire | Wire distribution | Paid (low cost) | Budget wire for routine milestones |

The highest-leverage PR asset EA could build Original research is the most reliable way to earn links from publications that do not otherwise cover outsourced accounting firms. Proposal: an annual CPG Finance Benchmark Report — survey 150–300 finance leaders at consumer-goods companies on trade-spend leakage, deduction write-off rates, month-end close times and cost-per-transaction benchmarks. No competitor in the analysed set publishes anything comparable. Trade press covers original data readily because it gives them a story they cannot get elsewhere, and a benchmark report earns citations passively for years. This is how a DR 24 site gets links from DR 80+ domains without paying for them — and it directly supports the trade-promotion keyword cluster identified in Section 4.4.

Owner: Mixed — see the tag above each sub-section below. This section spans technical SEO, content operations and analytics; do not assign it to a single person.

# 8.  Additional Improvement Recommendations

Talha Azeem + Usman Ali — server config, redirects, schema markup, Core Web Vitals

## 8.1  Technical foundation

- Fix the redirect and 404 losses first (Section 3.2). Restore /fractional-cfo-services/ and /fractional-cpg-cfo-services/ as live pages; resolve the UR 9.9 Cloudflare 404; eliminate redirect chains on the two UR 11.7 URLs. Days of work, disproportionate return.

- Resolve the HTTP/HTTPS duplication. The crawl returned 200 responses for both http:// and https:// versions of numerous pages. Every page should 301 to a single canonical HTTPS URL.

- Fix the eaccelerated.com redirect. It currently returns a 302 (temporary), which does not consolidate link equity. Change to 301.

- Resolve keyword cannibalisation. /blog/how-much-does-a-cpa-cost/ and /cpa-cost/ target near-identical intent and compete with each other; /inventory-management/ and /inventory-management-services/ duplicate; /blog/ and /blogs/ both exist. Consolidate and 301 the weaker URL in each pair.

- Implement schema markup: Organization, Service, FAQPage and BreadcrumbList. FAQ schema in particular wins SERP real estate on the question-format content recommended throughout.

- Run a full Ahrefs Site Audit to surface orphan pages, duplicate titles and Core Web Vitals issues beyond those identified here.

Najma Furqan + Lavi Shamoon, with Haroon & Adeela reviewing — editorial process, E-E-A-T bylines, refresh cycle

## 8.2  Content operations

- Establish a refresh cycle. Bench's top page is years old and still ranks because it is maintained. Budget 20% of content capacity for updating existing pages.

- Put real CPA bylines with credentials and photos on every piece. This is a YMYL category where Google weights demonstrable expertise heavily, and anonymous financial content is at a structural disadvantage.

- Make case studies indexable and specific, with named clients and quantified outcomes, linked from the relevant service pillar.

- Build two or three interactive tools — an outsourcing cost calculator, a trade-spend leakage estimator, a DSO benchmark tool. Tools earn links at a far higher rate than articles and give sales a follow-up reason.

- Consolidate the operating-income and managerial-accounting content into two strong pillar pages rather than the current scattered thin posts (see Section 4.1).

Abdullah Shekha (Analytics) — GA4, Google Search Console, Ahrefs Rank Tracker, CRM pipeline attribution

## 8.3  Measurement

- Connect Google Search Console to Ahrefs so query-level data supplements third-party estimates.

- Set up Ahrefs Rank Tracker with the full 19-domain competitor set so movement is visible weekly.

- Track average keywords-per-page as the primary architecture metric. Current baseline is roughly 2.5; target 20+.

- Track pipeline attribution, not just traffic. Traffic is the leading indicator; qualified enquiries are the goal.

- Report share of voice within the defined keyword universe rather than absolute traffic — the honest measure of competitive progress.

Tabish Khalid — emerging-channel monitoring; brief for the whole team

## 8.4  A note on AI search

Ahrefs now tracks citations in ChatGPT, Google AI Overviews, Perplexity and Copilot. An increasing share of B2B research begins in an AI assistant rather than a search box, and the content that gets cited there is structurally similar to what ranks well: clear definitions, original data and demonstrable expertise. The glossary and original-research recommendations serve both channels. EA should baseline its AI citation footprint now, while the category is uncontested.

Owner: Haroon (Leadership)  •  Skillset: resource allocation and capacity management. All nine roles filled, eight of them full-time — this section is now a capacity and risk review, not a hiring plan.

# 9.  Team Structure & Capacity Review

All nine roles are filled as of 23 August 2026, and eight are full-time dedicated resources. Committed capacity is roughly 8.3 FTE. This section records who owns what, and gives an honest assessment of where that capacity is likely to strain.

| Role | Assigned to | Responsibilities | Commitment |
| --- | --- | --- | --- |
| Head of SEO & Content | Tabish Khalid | Strategy, keyword roadmap, reporting, quarterly re-run of this document | Full-time |
| Technical SEO / Content Strategist | Talha Azeem | Architecture, silos, internal linking, Core Web Vitals, schema, redirect cleanup, disavow | Full-time |
| Web Developer | Usman Ali | Server config, redirect rules, canonical tags, schema deployment, page speed | Full-time |
| Content Strategy Execution / Editor | Najma Furqan | Briefs, editorial calendar, SME interviews, QC, CPA-literate review | Full-time |
| SME Writer | Lavi Shamoon | Content production across all six pillars | Full-time |
| CPA Reviewers | Haroon & Adeela | Technical sign-off, E-E-A-T bylines, SME interview subjects | Alongside exec duties |
| Digital PR / Link Acquisition | Syed Ali — Director of Marketing | Journalist outreach, directories, chambers, podcast booking | Full-time |
| Design / Data-viz | Hameed Ishaq — Designer | Infographics, report design, interactive calculators | Full-time |
| Analytics | Abdullah Shekha — Analyst / Supervisor | GSC / GA4 / Ahrefs dashboards, pipeline attribution | Full-time |

What this staffing level makes possible Eight full-time people plus two CPA reviewers is enough capacity to run every workstream in parallel rather than in sequence. The entire technical remediation block closes by 12 September; all fifteen striking-distance pages are optimised before the Q1 checkpoint; silo linking, Site Audit remediation and the full directory and chamber programme all land inside Q1. The binding question is therefore not whether there is enough capacity to execute. It is whether the one part-time step in the chain — CPA review — can keep pace with eight full-time people upstream, and whether content volume can match the pace everything else runs at. One thing staffing does not compress: Domain Rating moves by roughly a single point by 30 September. Disavow reprocessing is a Google-side delay of one to three months and no amount of headcount shortens it. Do in September what makes DR move in December — and do not read a near-flat DR at the first checkpoint as a team failure.

## 9.1  Capacity risks in the current allocation

Six risks are visible in the current allocation. They are the risks of a well-resourced programme rather than an under-resourced one, but each still needs an owner and a mitigation agreed at the kickoff (Action A2).

| Risk | Severity | Why it matters | Recommended mitigation |
| --- | --- | --- | --- |
| CPA review is the only part-time step in a full-time pipeline | High | Haroon and Adeela review alongside running the business. Every page in a YMYL category needs their sign-off, and eight full-time people upstream will generate work faster than two part-time reviewers can clear it. This is now the single narrowest point in the chain. | Agree a review SLA at kickoff — 48-hour turnaround, batched twice weekly in a protected slot. Tie publishing cadence to review capacity, not writing capacity. |
| The plan is under-scoped for the capacity now available | Medium-High | The 8–12 pieces/month target was sized for roughly 2 FTE of writing. EA now has a full-time writer and a full-time editor, plus technical capacity that frees up in October. The Section 11.2 targets are likely conservative. | Do not inflate the targets speculatively. Measure actual throughput through Q1, then re-baseline Q2 onward from observed data at the first quarterly review. |
| No redundancy — every function has exactly one owner | Medium-High | Nine dedicated people but zero overlap. A two-week absence by Talha, Lavi or Usman halts that workstream completely, and the shortfall surfaces in the metrics a quarter later. | Cross-train in pairs and document process: Najma as writing backup, Talha as analytics backup, Tabish as PR backup. Assign at kickoff (A2). |
| Syed Ali owns two overlapping outreach programmes | Medium | Sections 6 and 7 both target CFO Dive, Accounting Today and the trade press. Uncoordinated, the same editor gets pitched twice — which damages the relationship rather than building it. | One master outreach tracker covering both link and PR targets, deduplicated before any contact is made. |
| Technical load drops sharply after September | Medium | Remediation is heavily front-loaded. Talha and Usman are fully committed through September, then materially under-used unless Q2 work is assigned in advance. | Book them from October onto silo build (A21), interactive calculators (A29), schema expansion, page speed and full Site Audit remediation. |
| Faster publishing raises the accuracy risk | Medium | More capacity means more pages shipped per month. In a YMYL category, volume without review discipline is how factually wrong content reaches production — the one failure that damages EA's credibility with CFO buyers. | No page publishes without recorded CPA sign-off. Track review turnaround as a programme metric from Q1, not just output volume. |

## 9.2  The review bottleneck — now the narrowest point in the chain

Haroon and Adeela are the named CPA reviewers, and they are the only part-time step in an otherwise full-time pipeline. They review alongside running the business, which makes this the narrowest point in the chain regardless of how well everything upstream performs.

The arithmetic is worth stating plainly. Eight full-time people generate work upstream of a review step staffed by two people with competing executive priorities. If Lavi Shamoon and Najma Furqan sustain even 10 pieces per month, that is roughly 2.5 pieces per week requiring technical sign-off. At any realistic review pace this is manageable — but only if the time is genuinely protected and the turnaround is agreed rather than assumed.

The failure mode to watch for is subtle: content gets written on schedule, then queues waiting for review. Production looks healthy in the editorial calendar while the indexed-pages metric flatlines, and by the time the quarterly report surfaces it, a full quarter of publishing has been lost. It reads as a content problem when it is actually a review-capacity problem.

Recommended at kickoff: a 48-hour review SLA, reviews batched into two protected slots per week rather than handled ad hoc, and review turnaround tracked as a programme metric from Q1 alongside output volume. If the queue starts building, throttle publishing cadence to match review capacity rather than letting a backlog accumulate.

There is a second benefit worth capturing. A 30-minute recorded interview with Haroon or Adeela produces enough raw material for two or three genuinely differentiated articles — so the same time investment does double duty as quality control and as the source material that makes EA's content sound like EA rather than like every other outsourcing firm.

## 9.3  Capacity against workload, function by function

The department carries roughly 1.6x the capacity this workload requires — but the surplus is not evenly distributed, and that determines which timelines can run aggressively and which cannot.

| Function | Workload requires (FTE) | Capacity available | Ratio | Consequence |
| --- | --- | --- | --- | --- |
| Head of SEO & Content | 0.5–1.0 | 1.0 (Tabish Khalid) | Surplus | Weekly rather than monthly programme review |
| Technical SEO | 0.25 | 1.0 (Talha Azeem) | 4.0x | Remediation block runs two weeks, not five |
| Web Developer | 0.5 (implied) | 1.0 (Usman Ali) | 2.0x | No dev dependency on any action |
| Content Editor | 1.0 | 1.0 (Najma Furqan) | At parity | No slack — briefs and QC absorb the full role |
| SME Writing | 2.0 | 1.0 (Lavi Shamoon) | 0.5x | Under-resourced — the binding constraint |
| CPA Review | 0.2 | ~0.3 (Haroon & Adeela) | 1.5x | Marginal surplus; still the narrowest step |
| Digital PR / Links | 0.5 | 1.0 (Syed Ali) | 2.0x | Directories, TPM listings and chambers all inside Q1 |
| Design / Data-viz | 0.25 | 1.0 (Hameed Ishaq) | 4.0x | Calculators ship in Q2 |
| Analytics | 0.15 | 1.0 (Abdullah Shekha) | 6.7x | Tracking live in week one |
| TOTAL | 5.35 | ≈ 8.3 | ≈ 1.6x | Every workstream runs in parallel |

Four functions carry substantial surplus. Analytics at 6.7x what the workload needs, technical SEO and design at 4x, digital PR and development at 2x. Every timeline that depends on those functions runs at maximum pace in Sections 10 and 11 — technical remediation completes by 12 September, all partner directories and chamber memberships land in Q1, the interactive calculators ship in Q2, and tracking goes live in week one.

One function is under-resourced, and it is the one that drives most of the traffic metrics. The content workload requires roughly 2.0 FTE of writing and is staffed at 1.0 — Lavi Shamoon alone. Content volume is therefore the binding constraint on the whole programme, and no amount of surplus elsewhere fixes it. Najma Furqan and Talha Azeem both hold partial content remits and can absorb some production, which brings effective capacity close to requirement but not above it.

The honest implication: the targets in Section 11.2 are achievable on technical, link and infrastructure work with margin to spare. On content volume they are achievable but not comfortable. If one thing in this plan slips, it will be published-page count — which is why it appears as the earliest warning signal in the accountability map, and why adding a second writer is the single highest-value further investment available.

## 9.4  Deploying the technical capacity after September

Talha Azeem and Usman Ali are fully committed through September on remediation — ten actions inside five weeks. From October their load drops sharply, and two full-time technical resources without assigned work will drift toward low-value activity.

Book them in advance. The natural Q2 and Q3 workload is the silo internal-linking build (A21), the three interactive calculators (A29), full Site Audit remediation, schema expansion beyond the initial four types, and page-speed work. None of that is currently on the critical path, which is precisely why it will get skipped unless it is scheduled deliberately.

One further use of the spare capacity: the cross-training in risk three. Nine dedicated people with no functional overlap means every workstream has a single point of failure. October is the right window to document process and pair up backups, while the pressure is lower.

Owner: Tabish Khalid (Head of SEO & Content, programme owner)  •  Skillset: cross-functional programme management, stakeholder reporting. Requires Haroon's sign-off on targets.

# 10.  12-Month Roadmap

Paced to the capacity available (see Section 9.3). Quarter 1 is only five and a half weeks from baseline but carries the entire technical remediation block, Site Audit remediation, all fifteen striking-distance pages, silo linking and the full directory and chamber programme.

| Period | Focus | Target outcome |
| --- | --- | --- |
| Q1 (to 30 Sep 26) | Entire technical remediation block closed by 12 Sep; Site Audit remediation; all 15 striking-distance pages optimised; silo linking live; every partner directory, TPM listing and chamber claimed; benchmark survey fielded | DR 24→25; traffic 286→520; indexed pages 45→60 |
| Q2 (to 31 Dec 26) | Seven non-ranking service pages; interactive calculators shipped; glossary phase 1 (30 terms); six pillar pages; CPG Benchmark Report published | DR 25→32; traffic 520→1,600 |
| Q3 (to 31 Mar 27) | Podcast circuit; contributed columns; glossary to 60 terms; conversion optimisation across all money pages | DR 32→39; traffic 1,600→2,900 |
| Q4 (to 30 Jun 27) | Second research drop; refresh cycle on decaying content; deepen CPG/TPM/manufacturing silos | DR 39→45; traffic 2,900→4,800 |
| Q5 (to 30 Sep 27) | Glossary to 90 terms; vertical expansion; scale what the data shows is working | DR 45→50; traffic 4,800→7,500 |

## 10.1  The five things that matter most

- Disavow the toxic links and stop the vendor. Seventeen link-selling domains and roughly 30 directory/spam sites are the most likely cause of DR 24 on 861 referring domains. Nothing else works properly until this is done. Talha Azeem, by 5 September (A10).

- Recover the trapped equity. Two UR 11.7 redirects, a UR 9.9 404, and a UR 9.9 redirect on the fractional-CFO URL. Days of work for the highest return-per-hour in the entire plan. Talha Azeem and Usman Ali, by 5 September (A8, A11, A12).

- Optimise before you write. Fifteen pages in positions 11–28 covering 19,800 monthly searches, plus seven service pages that exist and do not rank for difficulty-0 terms. All cheaper than new content. Lavi Shamoon and Najma Furqan, across A19 and A23.

- Build clusters, not pages. Average keywords-per-page rising from roughly 2.5 to 20+ is the single metric that captures whether the architecture and content strategy are working.

- Take the niche before anyone else does. Roughly 7,000 monthly searches across CPG, trade promotion, manufacturing and e-commerce accounting at difficulty 0–20, with no competitor coverage. It is the only position in this market EA can defend on expertise rather than price — and it will not stay uncontested indefinitely.

Owner: Tabish Khalid (programme owner) + every named owner in the register below  •  Skillset: programme governance, KPI tracking, cross-functional accountability. This section is the tracking instrument — re-run and complete it at every quarter end.

# 11.  Action Plan & Quarterly Progress Tracker

How this section works Table 11.1 is the action register: every action point, the position responsible, what specifically must be delivered, and the date it is due. Table 11.2 projects where each critical statistic should stand at each quarter end IF the actions in 11.1 are completed on time. Table 11.3 maps each statistic back to the team accountable for it — so when a number misses its target at the next quarterly re-run, the shortfall points directly at the action that was not delivered. Table 11.4 is the blank scorecard to complete at the first checkpoint (30 September 2026). Baseline for every figure: 23 August 2026. Re-pull the same Ahrefs reports each quarter so the comparison is like-for-like.

## 11.1  Action register

Thirty-four actions against named individuals, ordered by delivery date. The highlighted block (A1–A22) is everything due by the first checkpoint on 30 September.

| # | Action point | Position responsible | Action required | Delivery date |
| --- | --- | --- | --- | --- |
| A1 | Terminate paid link-building vendor | Haroon (Leadership) + Tabish Khalid | Cancel any active contract; confirm no further link purchases in writing | 27 Aug 2026 |
| A2 | Programme kickoff and RACI sign-off | Tabish Khalid | Walk this document with all nine owners; confirm each accepts their actions | 27 Aug 2026 |
| A3 | Agree CPA review SLA | Haroon & Adeela + Najma Furqan | 48-hour turnaround; two protected review slots per week; sign-off recorded per page | 27 Aug 2026 |
| A4 | Assign cross-training backups | Tabish Khalid | Pair every function with a named backup — no workstream with a single point of failure | 29 Aug 2026 |
| A5 | Stand up tracking infrastructure | Abdullah Shekha | GSC↔Ahrefs connected; Rank Tracker loaded with 19-domain competitor set | 29 Aug 2026 |
| A6 | Fix eaccelerated.com redirect | Usman Ali + Talha Azeem | Change 302 to 301 so link equity consolidates | 29 Aug 2026 |
| A7 | Classify full referring-domain list | Talha Azeem | Export all 861 domains from Ahrefs; label keep / ignore / disavow | 2 Sep 2026 |
| A8 | Resolve UR 9.9 Cloudflare 404 | Usman Ali + Talha Azeem | Fix or redirect /cdn-cgi/l/email-protection | 2 Sep 2026 |
| A9 | Brief the 15 striking-distance pages | Najma Furqan | Write optimisation briefs with target keyword, format and internal links | 2 Sep 2026 |
| A10 | File disavow in Search Console | Talha Azeem | Submit domain-level disavow for link-sellers, PBNs and flagged spam | 5 Sep 2026 |
| A11 | Recover UR 11.7 redirect chains | Usman Ali + Talha Azeem | Restore or consolidate /accounts-payable/ and /general-accounting-and-bookkeeping/ | 5 Sep 2026 |
| A12 | Restore /fractional-cfo-services/ | Talha Azeem + Najma Furqan | Rebuild as live optimised page targeting 'fractional cfo' (14,000/mo) | 5 Sep 2026 |
| A13 | Resolve HTTP/HTTPS duplication | Usman Ali + Talha Azeem | 301 every http:// URL to its canonical https:// equivalent | 12 Sep 2026 |
| A14 | Resolve keyword cannibalisation | Talha Azeem + Najma Furqan | Consolidate 3 duplicate page pairs; 301 the weaker URL in each | 12 Sep 2026 |
| A15 | Implement schema markup | Usman Ali + Talha Azeem | Organization, Service, FAQPage, BreadcrumbList sitewide | 12 Sep 2026 |
| A16 | Claim software partner directories | Syed Ali | NetSuite, Sage Intacct, QuickBooks, Xero, Bill.com, Ramp, Brex listings live | 12 Sep 2026 |
| A17 | Claim TPM / CPG vendor listings | Syed Ali | Vividly, Cresicor and adjacent partner pages live | 19 Sep 2026 |
| A18 | Full Ahrefs Site Audit and remediation | Talha Azeem + Usman Ali | Orphan pages, duplicate titles, Core Web Vitals — uses freed technical capacity | 26 Sep 2026 |
| A19 | Optimise all 15 striking-distance pages | Lavi Shamoon + Najma Furqan | Expand and re-optimise the full set (19,800 combined monthly searches) | 30 Sep 2026 |
| A20 | Implement silo internal linking | Talha Azeem + Najma Furqan | Hub-and-spoke across all 6 pillars; breadcrumbs live | 30 Sep 2026 |
| A21 | Join chambers and associations | Syed Ali + Haroon | ChamberMaster network, ACG, AICPA, IMA, Consumer Brands Association | 30 Sep 2026 |
| A22 | Field CPG Benchmark survey | Syed Ali + Haroon | Design and distribute to 150–300 CPG finance leaders | 30 Sep 2026 |
| A23 | Optimise 7 non-ranking service pages | Lavi Shamoon + Najma Furqan | Manufacturing, e-commerce, Amazon, TPM, AP, AR, FP&A pages | 31 Oct 2026 |
| A24 | Build interactive calculators | Hameed Ishaq + Usman Ali | Outsourcing cost calculator, trade-spend leakage estimator, DSO tool | 30 Nov 2026 |
| A25 | Launch glossary phase 1 | Lavi Shamoon + Najma Furqan | 30 lowest-difficulty terms published and internally linked | 30 Nov 2026 |
| A26 | Publish CPG Finance Benchmark Report | Syed Ali + Hameed Ishaq | Design, publish, gate and pitch to trade press | 31 Dec 2026 |
| A27 | Build 6 pillar pages | Lavi Shamoon + Najma Furqan | 2,500–4,000 words each, one per silo | 31 Dec 2026 |
| A28 | Complete podcast circuit round 1 | Syed Ali | 8+ CFO / CPG-finance podcast appearances with show-note links | 31 Jan 2027 |
| A29 | Secure contributed columns | Syed Ali | Forbes / Entrepreneur / Inc. council placements live | 28 Feb 2027 |
| A30 | Glossary phase 2 | Lavi Shamoon + Najma Furqan | Expand to 60 terms; add templates | 31 Mar 2027 |
| A31 | Conversion optimisation on money pages | Najma Furqan + Abdullah Shekha | CRO pass on all commercial pages; refresh decaying content | 31 Mar 2027 |
| A32 | Second research drop | Syed Ali + Hameed Ishaq | Follow-up benchmark or vertical-specific study | 30 Jun 2027 |
| A33 | Glossary phase 3 and vertical expansion | Lavi Shamoon + Najma Furqan | Expand to 90 terms; deepen manufacturing and CPG silos | 30 Sep 2027 |
| A34 | Re-run this report each quarter | Tabish Khalid + Abdullah Shekha | Re-pull all Section 11 metrics; complete the scorecard; audit the register | Every quarter end |

Highlighted rows (A1–A22) are the Quarter 1 block, all due by 30 September 2026. Twenty-two actions in five and a half weeks is achievable only because every workstream runs in parallel. The technical remediation block closes by 12 September, which leaves the second half of the month for Site Audit work and silo linking rather than for catching up. If A1–A22 are not complete by 30 September, reset the December and March projections in Table 11.2 rather than carrying them forward.

## 11.2  Quarterly projection of critical statistics

Where each metric should stand at each quarter end if the action register is delivered on time. Targets are set to the capacity available rather than to a conservative baseline — they assume every workstream runs in parallel from week one.

| Critical statistic | Baseline 23 Aug 26 | Q1 end 30 Sep 26 | Q2 end 31 Dec 26 | Q3 end 31 Mar 27 | Q4 end 30 Jun 27 | Q5 end 30 Sep 27 |
| --- | --- | --- | --- | --- | --- | --- |
| Domain Rating (DR / DA) | 24 | 25 | 32 | 39 | 45 | 50 |
| Organic traffic / month (global) | 286 | 520 | 1,600 | 2,900 | 4,800 | 7,500 |
| Organic traffic / month (US) | 260 | 480 | 1,470 | 2,670 | 4,450 | 6,990 |
| Organic keywords (global) | 115 | 240 | 700 | 1,250 | 1,950 | 2,800 |
| Organic keywords (US) | 86 | 190 | 550 | 985 | 1,540 | 2,205 |
| Keywords ranked #1–3 | 16 | 34 | 105 | 205 | 370 | 570 |
| Keywords ranked #4–10 | 80 | 155 | 400 | 670 | 1,020 | 1,430 |
| Keywords in top 10 (total) | 96 | 189 | 505 | 875 | 1,390 | 2,000 |
| Est. traffic value / month | $1,467 | $2,900 | $8,500 | $16,000 | $28,000 | $46,000 |
| Referring domains (total) | 861 | 900 | 1,030 | 1,180 | 1,350 | 1,540 |
| Quality ref. domains (DR30+, dofollow) | ~35 | 75 | 160 | 260 | 370 | 490 |
| Avg. keywords per ranking page | ~2.5 | 4 | 8 | 13 | 18 | 23 |
| Live indexed content pages | ~45 | 60 | 100 | 155 | 210 | 260 |

- Domain Rating (DR) is Ahrefs' equivalent of Domain Authority. If EA also tracks Moz DA, expect it to move on a similar curve but roughly 3–6 points higher at each checkpoint — the two scales are not interchangeable, so pick one and report it consistently. DR 50 by September 2027 would put EA ahead of D&V Philippines (51 today) and NOW CFO (46) — ambitious, and dependent on the link programme running at the full-time pace the staffing now allows.

- DR shows only a single point of movement by 30 September. Disavow reprocessing takes one to three months, so most of September's work registers in December. The one point reflects the partner directories and TPM listings landing mid-month — real new quality links. Do not expect more than a point or two at the first checkpoint.

- “Quality referring domains” means DR 30+, dofollow, non-spam. The ~35 baseline is estimated from a top-100 sample rather than a full census; the first tracking run should establish the exact figure and restate the baseline if it differs materially.

- Referring domains total barely moves in Q1 because disavowal does not remove domains from Ahrefs — it only tells Google to ignore them. Judge link work on the quality row, not the total row.

- Content-driven rows carry more risk than the rest. Indexed pages, organic keywords and keywords #1–3 all depend on writing throughput, and SME writing is the one function staffed below what the workload requires (Section 9.3). The technical, link and infrastructure rows have capacity margin; these do not.

- These are planning targets, not forecasts. They assume the action register is delivered, competitor behaviour stays broadly stable, and no major algorithm disruption occurs. Revise them at each quarter end rather than treating a miss as automatic failure — but revise them explicitly, with a stated reason.

## 11.3  Accountability map — whose miss shows up where

This is the mechanism that makes the document self-policing. Each statistic in Table 11.2 now maps to a named individual rather than a function. When the next quarterly re-run shows a metric below target, this table names the person and the specific actions to investigate first.

| Critical statistic | Owner accountable | What a miss against target indicates |
| --- | --- | --- |
| Domain Rating (DR / DA) | Talha Azeem (disavow) + Syed Ali (acquisition) | Disavow not filed, or link acquisition stalled. Check A10, A16, A17, A21 first. |
| Quality referring domains | Syed Ali | Partner directories and chamber memberships not claimed. Directly traceable to A16, A17, A21. |
| Referring domains (total) | Syed Ali | Outreach volume below plan; podcast and column pipeline empty (A28, A29). |
| Keywords ranked #1–3 | Lavi Shamoon + Najma Furqan | Striking-distance optimisation not executed or ineffective. Traceable to A19, A23. |
| Organic keywords (total) | Lavi Shamoon + Najma Furqan | Publication cadence below plan. Traceable to A25, A27, A30. |
| Avg. keywords per ranking page | Talha Azeem + Najma Furqan | Silo linking not implemented, or thin pages still being published. Traceable to A20. |
| Live indexed content pages | Lavi Shamoon | Production throughput below plan — the earliest warning signal of all, and the flagged capacity risk. |
| Est. traffic value / month | Najma Furqan + Tabish Khalid | Output skewed to informational terms; commercial money pages neglected. |
| Organic traffic (US) | Najma Furqan + Tabish Khalid | Targeting drifting off-market, or content not matching US buyer intent. |
| Organic traffic (global) | Composite — all owners | Lagging indicator. Diagnose using the rows above rather than acting on this directly. |
| Technical health (crawl, speed, schema) | Talha Azeem + Usman Ali | Site Audit remediation and schema deployment not completed. Traceable to A15, A18. |
| Actions delivered on time | Tabish Khalid | Programme management gap — actions slipping without escalation. |

Reading a missed target correctly Not every miss is a performance failure, and treating it that way will produce defensive reporting rather than useful reporting. Diagnose in this order: (1) Was the underlying action in Table 11.1 actually delivered, on time and to spec? (2) If yes, was the assumption behind the target wrong — e.g. difficulty higher than Ahrefs estimated? (3) If both check out, look for an external cause — an algorithm update, or a competitor investing heavily in the same terms. Only the first case is an accountability issue. The other two are planning corrections, and the projection should be revised openly rather than quietly carried forward. One caution: leading indicators move before lagging ones. Live indexed content pages and quality referring domains respond within weeks; Domain Rating and traffic lag by one to two quarters. Judge Q1 on the leading rows only.

## 11.4  Quarter 1 scorecard — complete at 30 September 2026

Print or copy this table at each quarter end. Re-pull every figure from the same Ahrefs reports used for the baseline, enter the actual, calculate the variance, and assign a RAG status. Repeat with the next column of Table 11.2 for subsequent quarters.

| Critical statistic | Target 30 Sep 26 | Actual | Variance | RAG | Owner accountable |
| --- | --- | --- | --- | --- | --- |
| Domain Rating (DR / DA) | 25 |  |  |  | Talha / Syed Ali |
| Organic traffic / month (global) | 520 |  |  |  | All owners |
| Organic traffic / month (US) | 480 |  |  |  | Najma / Tabish |
| Organic keywords (global) | 240 |  |  |  | Lavi / Najma |
| Keywords ranked #1–3 | 34 |  |  |  | Lavi / Najma |
| Keywords in top 10 (total) | 189 |  |  |  | Lavi / Najma |
| Est. traffic value / month | $2,900 |  |  |  | Najma / Tabish |
| Referring domains (total) | 900 |  |  |  | Syed Ali |
| Quality ref. domains (DR30+, dofollow) | 75 |  |  |  | Syed Ali |
| Avg. keywords per ranking page | 4 |  |  |  | Talha / Najma |
| Live indexed content pages | 60 |  |  |  | Lavi Shamoon |
| Actions A1–A22 completed on time | 22 of 22 |  |  |  | Tabish Khalid |

RAG thresholds:

- Green — actual is 95% or more of target.

- Amber — actual is 80–94% of target. Investigate; corrective action agreed at the quarterly review.

- Red — actual is below 80% of target. Escalate to Leadership; the responsible team presents a recovery plan before the next quarter begins.

## 11.5  Governance — running the quarterly review

- Re-pull the data (Analytics / SEO Team). Same Ahrefs reports, same settings — subdomains mode, both protocols, US country filter where the metric specifies US. Consistency matters more than precision.

- Complete the scorecard (Head of SEO & Content). Fill actual, variance and RAG for every row. Do not omit rows that look bad.

- Audit the action register (Head of SEO & Content). Mark each action delivered / late / not started, with the date. This is what separates an execution failure from a planning error.

- Review with owners (all teams + Leadership). Walk Table 11.3 for every amber and red. Each accountable team explains the cause and proposes the correction.

- Restate the next quarter's targets (Head of SEO & Content). Carry forward, or revise with a written reason. Revised targets are legitimate; silently dropped ones are not.

- Re-issue this document (Head of SEO & Content). Update Table 11.2 with actuals alongside targets so the document accumulates a track record rather than being replaced each time.

The point of this structure: an owner who does not deliver their actions will see the consequence appear in a specific, named statistic at the next run — not in a general sense that progress is slow. Syed Ali's inactivity surfaces as flat quality-referring-domains. Lavi Shamoon's shortfall surfaces as flat indexed pages and keywords. Talha Azeem's surfaces as flat average-keywords-per-page and a DR that never moves. Najma Furqan's surfaces as traffic value lagging traffic volume. The numbers do the supervising.

One fairness caveat, given that names are attached: the capacity risks in Section 9.1 were identified before execution began, and the targets assume the staffing level described in Section 9.3. If Lavi Shamoon misses the indexed-pages target while writing is staffed at half what the workload requires, or if content queues behind CPA review capacity, those are allocation failures rather than individual performance failures. Check Sections 9.1 and 9.3 before attributing a miss to the person named in Table 11.3.

Addendum

Owner: Tabish Khalid + Haroon — Competitive Intelligence  •  Skillset: market positioning analysis, geographic traffic segmentation, commercial-intent assessment. Reference material — no scheduled actions arise directly from this addendum.

# Addendum A.  D&V Philippines vs. Expertise Accelerated

D&V Philippines (dvphilippines.com) is a Manila-based, CPA-led finance and accounting BPO. Its service mix — bookkeeping, AP/AR, financial reporting, CFO support, audit support, fund management — overlaps with EA's almost completely, and it targets the same two personas: CFOs extending their accounting department, and professional-services firms augmenting capacity. It is a closer like-for-like competitor than Bench or Pilot, which is why it warrants separate treatment.

## A.1  Headline comparison (global)

| Metric | D&V Philippines | Expertise Accelerated | Gap |
| --- | --- | --- | --- |
| Domain Rating | 51 | 24 | D&V +27 points |
| Monthly organic traffic (global) | 4,783 | 286 | D&V 16.7x |
| Organic keywords (global) | 633 | 115 | D&V 5.5x |
| Keywords ranked #1–3 | 168 | 16 | D&V 10.5x |
| Referring domains | 1,098 | 861 | D&V +237 (1.3x) |
| Total backlinks | 2,425 | 1,982 | D&V +443 (1.2x) |
| Est. monthly traffic value | $7,366 | $1,467 | D&V 5.0x |
| Paid search traffic | 0 | 0 | Neither runs PPC |

The highlighted rows are the important ones. D&V has only 27% more referring domains and 22% more backlinks than EA, yet more than double the Domain Rating and nearly 17x the traffic. Link volume is not what separates these two companies — link quality is. This is the same diagnosis as Section 5, seen from the outside.

## A.2  The 16.7x gap dissolves under geographic analysis

| Country | Monthly traffic | % of total | Est. value/mo | % of value |
| --- | --- | --- | --- | --- |
| Philippines | 3,926 | 82.1% | $251 | 3.4% |
| United States | 593 | 12.4% | $6,906 | 93.7% |
| India | 59 | 1.2% | $10 | 0.1% |
| Australia | 44 | 0.9% | $46 | 0.6% |
| Canada | 20 | 0.4% | $36 | 0.5% |
| All others | 141 | 3.0% | $117 | 1.6% |

82% of D&V's traffic is Philippine-domestic, and Ahrefs values all 3,926 of those visits at $251 per month — roughly six cents per visit. The 593 US visits, just 12% of volume, carry $6,906 of the $7,366 total: 94% of the commercial worth of their search footprint sits in one-eighth of their traffic.

The comparison that actually matters United States organic performance, head to head: • Monthly organic traffic — D&V 593 vs. EA 260 (2.3x, not 16.7x) • Organic keywords — D&V 126 vs. EA 86 (1.5x) • Est. monthly traffic value — D&V $6,906 vs. EA $1,394 (5.0x) EA is roughly one doubling away from parity with D&V in its actual target market. On the Table 11.2 projection, EA overtakes D&V's current US traffic (593/mo) inside Q1, before the 30 September checkpoint.

| US-only metric | D&V | EA | Multiple |
| --- | --- | --- | --- |
| Monthly organic traffic (US only) | 593 | 260 | 2.3x |
| Organic keywords (US only) | 126 | 86 | 1.5x |
| Est. monthly US traffic value | $6,906 | $1,394 | 5.0x |

## A.3  Where D&V's traffic actually comes from

| Page | Traffic | Top keyword | Volume | What it attracts |
| --- | --- | --- | --- | --- |
| /about-us/careers | 1,747 | d&v philippines | 2,000 | Recruitment — not a buyer |
| / (homepage) | 719 | d&v philippines | 2,000 | Branded / navigational |
| /blog/…big-four-accounting-firms | 484 | big 4 accounting firms | 2,200 | Students & job seekers |
| /blog/importance-of-hmo | 179 | hmo meaning in work | 1,500 | PH employee benefits |
| /blog/…ease-of-doing-business-law | 167 | ease of doing business act | 3,000 | PH regulation |
| /understanding-the-train-law | 104 | train law meaning | 1,300 | PH tax law |
| /blog/create-more-law-philippines | 84 | create more | 700 | PH tax law |
| /accounting-financial-services/outsourced-bookkeeping | 74 | bookkeeping services philippines | 150 | Commercial — buyer intent |
| /infographics/types-of-accounting-errors | 66 | transposition error in accounting | 100 | Educational |
| /blog/…cost-vs-management-accounting | 63 | cost accounting and control | 800 | Students |

Their largest single page is the careers page at 1,747 visits — 37% of their entire global traffic — driven by people searching the brand name looking for work in Manila. Their #3 page targets “big 4 accounting firms,” which attracts accounting students. Four more of the top ten cover Philippine tax and labour law. Exactly one page in the top ten carries buyer intent, at 74 visits.

Interpretation: D&V is winning employer-brand and local-authority search in the Philippines, which is rational for a company whose binding constraint is recruiting accountants. They are not out-executing EA on US demand generation. EA should not benchmark against their headline traffic number.

## A.4  Where D&V genuinely beats EA — and what to copy

In the US, D&V owns a tight cluster of geo-modified commercial keywords, almost all at keyword difficulty 0–2:

| Keyword (US) | Volume | D&V position | Difficulty |
| --- | --- | --- | --- |
| accounting outsourcing philippines | 200 | #1 | 0 |
| outsource accounting philippines | 200 | #1 | 0 |
| accounting outsourcing services philippines | 200 | #1 | 0 |
| accounting outsourcing manila | 200 | #3 | 0 |
| accounting outsourcing in the philippines | 150 | #1 | 0 |
| bookkeeping services philippines | 150 | #3 | 0 |
| outsourced accounting philippines | 150 | #2 | 0 |
| offshore accounting philippines | 100 | #1 | 0 |
| outsourced accountant philippines | 100 | #1 | 0 |
| cloud accounting vs traditional accounting | 100 | #1 | 2 |
| accounting services philippines | 70 | #2 | 17 |

This is the most transferable lesson in the study. D&V identified a narrow, uncontested, commercially-loaded keyword family — “accounting outsourcing + [location]” — and took the top three positions across every variant. The difficulty scores are effectively zero. There was no authority barrier; they simply built the pages and nobody else had.

EA's equivalent uncontested cluster EA's analogue is vertical specialism rather than geography. Verified Ahrefs volumes for the white space: • Manufacturing & inventory — 3,490 combined monthly searches, difficulty 0–20 • Controllership & FP&A — 1,350 combined, difficulty 0–14 • Trade promotion & deduction — 1,050 combined, difficulty 1–6 • E-commerce & Amazon — 950 combined, difficulty 0–8 Total: roughly 7,000 monthly searches at near-zero competition — and EA already has published pages for most of these topics that simply are not optimised to rank. Full detail in Section 4.4; the build actions are A23 and A27 in the register, owned by Lavi Shamoon and Najma Furqan.

## A.5  Verdict on D&V

- Ahead of EA on: domain authority (51 vs 24), commercial keyword ownership in their chosen niche, content volume, and consistent top-3 positioning.

- Not meaningfully ahead on: link acquisition volume (1,098 vs 861 referring domains), US buyer reach (593 vs 260 visits), or paid search (neither runs any).

- Structurally weaker than EA on: positioning. Their entire keyword strategy anchors to “the Philippines” — competing on offshore labour cost. EA's CPG and manufacturing specialism is a defensible, higher-margin position that cannot be commoditised the same way.

- Their vulnerability: 82% of their traffic has no commercial value, and brand-driven careers traffic inflates every headline metric. A competitor reading only the top-line number would substantially over-estimate them.

Tracking note (Tabish Khalid, each quarter): re-pull D&V's figures at each quarterly review alongside EA's. The metric to watch is US organic traffic, not global — if D&V's US figure climbs while EA's does too, the gap is closing on merit; if D&V's global figure climbs while US stays flat, they are simply recruiting harder in Manila and it is not a competitive threat. Add a D&V row to the Section 11.4 scorecard so the comparison is recorded each quarter rather than reconstructed.

Addendum

Owner: Every named individual below  •  Read your own brief, and read the brief of anyone you depend on. Executive support requests are collected in B.9 for Haroon to action at kickoff.

# Addendum B.  Direct Briefs to Each Owner

This addendum speaks to each owner directly. Each brief names the specific risk attached to that role, what to prioritise in the first weeks, who they must work with, and what they should ask the executive team for. The tone is deliberately candid — the plan only works if each person knows precisely where their own failure mode sits.

None of what follows is a judgement on past performance. These are structural risks that come with each seat in this particular plan.

## B.1  Tabish Khalid — Head of SEO & Content

Where you are exposed:  You own 34 actions across eight other people and no formal authority over any of them. The failure mode for this role is drifting into status reporting — collecting updates, publishing a summary, and calling that programme management. Nobody else can see the dependency chain, so if you are not actively sequencing work, the team will optimise locally and the programme will stall globally. You also own the quarterly re-run (A34), which is the first thing that gets deferred when a quarter-end is busy.

Urgent focus:  Run the kickoff (A2) as a commitment exercise, not a briefing. Every owner accepts their actions and dates in writing. Then build one shared tracker that everyone updates — not eight private lists. Chase the CPA review SLA (A3) personally; it is the constraint nobody else owns and the one most likely to be quietly skipped.

Cross-functional:  You are the only person who sees across all three workstreams, so sequencing is your job alone. Talha's silo linking (A20) is worthless until Lavi's pages exist. Syed Ali's outreach wastes goodwill if the landing pages he points to are still thin. Hameed needs six weeks' notice on the benchmark report, not two. Nobody else will spot these collisions.

Ask the executive team for:  Explicit authority from Haroon to escalate and to re-prioritise across functions. Without it you are coordinating peers with no lever, and the first time two owners disagree the programme stops.

## B.2  Talha Azeem — Technical SEO / Content Strategist

Where you are exposed:  You carry the tightest window in the plan — ten actions inside two weeks — and the highest-consequence one. The risk is not missing the deadline; it is hitting it with work that looks complete and is not. A disavow covering only the fifty domains named in this report, or a redirect map that resolves the obvious chains and leaves the rest, will read as done and will not move Domain Rating. A second exposure sits later: once remediation closes your load drops sharply, and the content-strategist half of your title has no assigned work.

Urgent focus:  The disavow (A10) is the single highest-value action in this document. Be exhaustive — classify all 861 referring domains, not the fifty already identified. Then the UR 11.7 recovery and the fractional-CFO URL restoration, which together release more accumulated equity than any content work will generate this quarter.

Cross-functional:  Five of your actions require Usman Ali. Book his time as a block now rather than requesting it ticket by ticket — that pattern is how two-week windows become six-week ones. Silo linking (A20) needs Najma's content map before you can start; agree the format with her in week one.

Ask the executive team for:  Google Search Console admin access on day one. If that takes two weeks to arrange, the disavow slips and the whole Q1 sequence slips with it. Flag it at kickoff, not when you are blocked.

## B.3  Usman Ali — Web Developer

Where you are exposed:  Five actions depend on you inside the first three weeks, and you are the newest addition to this plan. The risk is treating these as routine tickets. A 301 implemented without preserving the existing chain, or schema deployed with the wrong entity types, will pass every functional test and fail silently in search — nobody discovers it until a quarterly report shows a metric that never moved.

Urgent focus:  The eaccelerated.com 302→301 change (A6) is close to a one-line fix and is worth more than several weeks of content work, because it consolidates link equity that is currently being discarded on every request. Do it first. Then the Cloudflare 404 and the HTTP/HTTPS canonicalisation, which is the largest duplication problem on the site.

Cross-functional:  Talha specifies and you implement — but you are closer to the server than he is, so push back when a specification looks wrong rather than implementing it faithfully. On the calculators (A24) you and Hameed need to agree the build split early; design handing over a finished visual with no technical input is how those projects overrun.

Ask the executive team for:  A staging environment and an agreed rollback plan before touching redirects at scale. Sitewide redirect changes on production without a way back is the one action in this plan that could do real damage.

## B.4  Najma Furqan — Content Strategy Execution / Editor

Where you are exposed:  You sit between a single writer and two part-time reviewers, which makes it very easy for this role to become queue management rather than editing. Your first deliverable is also the highest-leverage one: fifteen briefs due 2 September (A9). If those are thin, everything downstream is thin, and no amount of writing or reviewing quality recovers it.

Urgent focus:  The briefs. Each one needs the target keyword, the SERP format you actually observed rather than assumed, a word count, the internal links in and out, and the specific question the page must answer. Look at what currently ranks for each term before writing the brief — the recurring error identified in Section 4.5 is writing service-page copy for informational queries, and briefs are where that gets prevented.

Cross-functional:  You are the interface between Lavi and the CPA reviewers, and how you manage that determines whether the review step becomes a bottleneck. Batch submissions into the two agreed weekly slots; never send pages one at a time. Coordinate with Talha so his internal linking structure matches your content map rather than being retrofitted to it.

Ask the executive team for:  Formal protection of the CPA review slots. You will be the first to see the queue building, and you need Haroon's backing to hold the line when review time gets squeezed by client work.

## B.5  Lavi Shamoon — SME Writer

Where you are exposed:  You are the binding constraint on this entire programme. Writing is staffed at one person against a workload sized for two, and the metric most likely to miss — live indexed content pages — is yours. The real risk is not effort; it is that volume pressure quietly degrades accuracy, and in a category where CFOs are the buyers, one factually wrong article costs more credibility than ten good ones earn.

Urgent focus:  All fifteen striking-distance pages by 30 September (A19). These are expansions and re-optimisations of pages that already exist and already rank on page two — considerably faster than writing from scratch, and they cover 19,800 monthly searches. Get them done before anything new is started.

Cross-functional:  Treat Haroon and Adeela as sources, not just approvers. A thirty-minute recorded interview gives you enough material for two or three genuinely differentiated articles, and it is the difference between EA-specific content and something any outsourcing firm could publish. Never start writing without a brief from Najma — if a brief is vague, send it back.

Ask the executive team for:  Honest capacity feedback, early. Establish your genuine sustainable rate during September and report it in week three — not in December. A second writer is already identified as the highest-value further investment, and that conversation is far easier with three weeks of real throughput data behind it.

## B.6  Syed Ali — Director of Marketing (Digital PR & Link Acquisition)

Where you are exposed:  You own two programmes — Sections 6 and 7 — that target overlapping publications. Run uncoordinated, you will pitch the same editor twice within a month, which damages a relationship rather than building one. Your second exposure is pacing: the easy wins are front-loaded and the hard ones are not. Directories can be claimed in days; earned press in CFO Dive takes months of relationship work, and if you do not start that in September it will not land in Q1 of next year.

Urgent focus:  Software partner directories and TPM vendor listings by mid-September (A16, A17). These are free, permanent, topically exact, and require nothing but completing forms — the highest return-per-hour available to anyone on this team. Then chambers and associations (A21): NOW CFO earned over 140 links through exactly this channel.

Cross-functional:  Maintain one master outreach tracker covering both link and PR targets, deduplicated before any contact. Your outreach only converts if the pages you point to are live and good — check with Najma before pitching anything. Give Hameed six weeks on the benchmark report, and hold yourself to the survey close date because his timeline depends entirely on yours.

Ask the executive team for:  Haroon's name and personal introductions for association and chamber approaches. A Director of Marketing gets a different reception than a founder does, and this is the cheapest acceleration available in the whole link programme.

## B.7  Hameed Ishaq — Designer

Where you are exposed:  Your work is back-loaded and almost entirely dependent on other people's timelines. If the benchmark survey closes late, your report design compresses, and you will have quiet weeks in September followed by an impossible crunch in December. Waiting for inputs is the failure mode here.

Urgent focus:  Do not wait for the survey to close. Build the report template, the chart library and the calculator UI shells during September while data collection is still running, so that when the data arrives you are populating a finished design rather than starting one. Use the quiet weeks deliberately.

Cross-functional:  The three calculators (A24) need Usman to build — agree who owns which layer in week one, because design-then-handover is how these projects overrun. Syed Ali controls the survey timeline that gates your biggest deliverable; get his committed dates in writing and escalate early if they move.

Ask the executive team for:  The brand asset library and design system if one exists, or two days to build one. Every infographic, report and calculator in this plan should look like it came from the same company, and that is far cheaper to establish now than to retrofit across a year of output.

## B.8  Abdullah Shekha — Analyst / Supervisor

Where you are exposed:  Your core deliverable finishes first and your role is the easiest in the team to under-use. Tracking goes live in week one — and then the risk is becoming a report generator rather than an analyst, producing dashboards nobody acts on. You have the most spare capacity of anyone here and the least prescribed work to fill it.

Urgent focus:  Tracking infrastructure by 29 August (A5) — nothing in Section 11 can be measured until it exists, so this genuinely blocks the programme's ability to know whether it is working. Then establish the exact quality-referring-domains baseline, which is currently an estimate from a sample rather than a full census.

Cross-functional:  You supply the evidence for every quarterly review, so agree metric definitions with Tabish now. When a number is disputed in December, the argument is always about definition rather than data — pre-empt it. Give Talha and Syed Ali weekly visibility rather than quarterly, so they can correct course inside the quarter.

Ask the executive team for:  CRM access. Traffic is the leading indicator but qualified enquiries are the actual goal, and nobody in this team can currently connect the two. You are the only person positioned to build that link, and it is what turns this from an SEO report into a pipeline report.

## B.9  Haroon & Adeela — CPA Review and Executive Oversight

Where you are exposed:  You are the narrowest step in a full-time pipeline, reviewing alongside running the business. The failure mode is not refusing to review — it is reviewing late, repeatedly, until a quarter of publishing has been lost. Because the delay appears downstream, it will present as a content problem and Lavi will absorb the blame for a queue he does not control. Haroon additionally holds four roles here: programme sponsor, CMO, reviewer and escalation point, and the reviewer role is the one most easily displaced by the other three.

Urgent focus:  Agree the review SLA (A3) and then defend it. Two fixed slots per week, 48-hour turnaround, sign-off recorded per page. Fixed slots beat good intentions — this is a calendar problem, not a willingness problem.

Cross-functional:  Work in batches with Najma rather than page by page. Make yourselves available as interview subjects for Lavi as well as reviewers; it is the highest-leverage use of your expertise and it is what makes EA's content sound like a firm that actually does this work.

What the team needs from you at kickoff:  Five requests are collected across the briefs above and each one blocks someone. Tabish needs explicit authority to escalate and re-prioritise across functions. Talha needs Search Console admin access on day one. Usman needs a staging environment and rollback plan. Syed Ali needs your name and introductions for associations and chambers. Abdullah needs CRM access. Granting these at the kickoff costs one meeting; granting them reactively costs weeks.

The one thing every owner should take from this addendum This plan does not fail through anyone doing their own job badly. It fails at the handoffs — briefs that arrive vague, developer time that is requested rather than booked, outreach that points at pages which are not ready, and review that happens eventually rather than on a schedule. Every brief above names the person you depend on and the person who depends on you. Read your own, then read theirs. The quarterly numbers in Section 11 will show whether those handoffs worked long before anyone can explain away a missed target.

All figures in this report were pulled live from Ahrefs on 22–23 August 2026 and are verifiable in the Ahrefs interface. Traffic and keyword figures are Ahrefs estimates. Volume, difficulty and CPC data are for the United States market. Baseline date for all Section 11 tracking: 23 August 2026.